## Sheet1
Order | Job | Low | Most likely | High | Actual Days | Due Date | Duration | When Done | Due | Days Late
9 | 1 | 6 | 11 | 16 | 10.1826 | 31 | 8.3532 | 8.3532 | 15 | 0
8 | 2 | 5 | 6 | 13 | 11.0974 | 46 | 9.3152 | 17.6684 | 16 | 1.6684
5 | 3 | 5 | 8 | 13 | 6.6022 | 52 | 5.7616 | 23.43 | 23 | 0.43001
10 | 4 | 6 | 9 | 11 | 10.5862 | 33 | 7.7944 | 31.2244 | 24 | 7.2244
4 | 5 | 5 | 6 | 8 | 5.7616 | 23 | 10.5862 | 41.8106 | 33 | 8.8106
2 | 6 | 6 | 9 | 15 | 9.2186 | 58 | 11.0974 | 52.908 | 46 | 6.908
3 | 7 | 6 | 10 | 15 | 11.6185 | 79 | 6.6022 | 59.5102 | 52 | 7.5102
6 | 8 | 4 | 9 | 16 | 9.3152 | 16 | 9.2186 | 68.7288 | 58 | 10.7288
1 | 9 | 5 | 7 | 11 | 8.3532 | 15 | 10.1826 | 78.9114 | 31 | 47.9114
7 | 10 | 5 | 8 | 10 | 7.7944 | 24 | 11.6185 | 90.5299 | 79 | 11.5299
Total Days Late
102.7215
Mean days late
89.6374
Mean days late around 90

## ro_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 102.7215 | 1 | 0.5 |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 3 |  | RISKOpt Tag | TRUE |  | Out Stats |  |  |  |  | VERSION 6.0 SETTINGS | EFFICIENT FRONTIER |  | EF Stopping Conditions
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations - Sim Stopping (legacy setting used in v5 and earlier)) | 1000 |  | Mean | Creation Version | 7.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence | Optimization Engine | 0 | Analysis Type (Standard vs. Efficient Frontier) | 0 | EF Stop on Trials | TRUE
Trial Count Stopping (enabled, trial count) | TRUE | 1000 |  |  | Before Recalc (enabled, macro), starting with v6 RISKOptimizer uses corresponding @RISK macro | FALSE |  | Number Formatting Cell (introduced in v5) |  |  | Sim. Stopping Mode, Tolerance (legacy settings used in v5 and earlier) | 1 | 0 | Std. Dev. | Required Version | 1.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed | Mutation Rate (becoming a single settings for all adjustable cell groups) | 0.1 | EF Item to Constrain |  | EF Trial Count | 250
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro), starting with v6 RISKOptimizer uses corresponding @RISK macro | FALSE |  |  |  |  | Same Seed Each Simulation (this was used in RISKOptimizer version 5 and earlier) | TRUE |  | Min | Recommended Version | 1.0.0 |  | Crossover Rate (becoming a single settings for all adjustable cell groups) | 0.5 | EF Constraint Minimum |  | EF Stop on Time | FALSE
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 100 | 0.01 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type (this was used in RISKOptimizer version 5 and earlier) | 3 |  | Max | Last Modified by Version | 7.5.0 |  | Genetic Operators (becoming a single settings for all adjustable cell groups) | 1,1,1,1,1,1,1,1,1,1,1 | EF Constraint Maximum |  | EF Time Duration | 15
Formula Stopping (enabled, formula) | FALSE |  |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro), starting with v6, this is legacy setting | FALSE |  |  | Genetic Algorithm - Discrete Variable Warning Shown |  |  | Stopping on Projected Convergence (added in version 6; other simulation runtime settings got moved to @RISK) | TRUE | EF Formula for Dtools |  | EF Time Unit | 2
Population Size | 50 | [9 empty] | Macro After Simulation (enabled, macro), starting with v6, this is legacy setting | FALSE |  |  | ColorOptimizationCells Called | TRUE | [5 empty] | EF Stop on Progress | FALSE
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1 | [14 empty] | EF Trials (Progress) | 100
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE | [15 empty] | EF Max. Change (Progress) | 0.01
Stop on Errors (before v5: Pause on Errors) | FALSE | [20 empty] | EF Max. Change is Percent (Progress) | TRUE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting); this setting no longer used staring with version 6 | TRUE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [22 empty] | # Constraints | 0
Method + #Operators(Legacy) | Mutation Rate (Legacy) | Crossover Rate (Legacy) | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [13 empty] | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter | Precision (added 6.0) | RO Auto Eval Time (added 6.0) | Is Disabled | Use for EF | EF Settings Have Been Defined | EF Location of Constraining Values | EF Min Constraining Value | EF Max Constraining Value | EF # of Constraining Values Between Min and Max | EF Range with Constraining Values | EF # of Constraining Values Listed
ORDER11 | 0.1 | 0.5 |  |  |  | 1 | #VALUE! |  |  |  |  | FALSE
DEFAULT PARENT SELECTION
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH