## Sheet1
simtable |  |  | Tennistourney.xlsx |  | Critical Acitivity: If activity takes .01days longer | [5 empty] | 60 times we add .01 t olength of project |  |  | q11 would have 60(.01)/100
#NAME? |  |  | Project Management.docx |  | does the project length increase |  |  | by .01days |  |  | 40 times we add 0 |  |  | added and then divided by .01
|  |  | Use RISKPERT to model duration of activity | [7 empty] | Probability D is critical |  |  | gets 60/100
[11 empty] | run 100 iterations | [5 empty] | Only ammal that can fly
|  | Activity | Predecessors | Min | Most Likely | Max | Duration |  |  |  | suppose 60 times Project takes .01 | [5 empty] | Bat
1 | A | Negotiate for location |  | 1 | 2 | 4 | #NAME? | Negotiate for location |  |  | more days in Sim 4 | [5 empty] | Mammal highest blood pressure
2 | B | Contact seeded players |  | 5 | 8 | 12 | #NAME? | Contact seeded players | Time |  |  | Activity | mean time +delta | Prob critical |  |  | Giraffe
3 | C | Plan promotion | A | 2 | 3 | 6 | #NAME? | Plan promotion | A | #NAME? | A | 1 | #NAME? | #NAME? | 20.5708 | #NAME?
4 | D | Locate Officials | C | 1 | 2 | 5 | #NAME? | Locate Officials | B | #NAME? | B | 2 | #NAME? | #NAME? | 20.5612 | #NAME?
5 | E | Send RSVPs | C | 6 | 10 | 12 | #NAME? | Send RSVPs | C | #NAME? | C | 3 | #NAME? | #NAME? | 20.5708 | #NAME?
6 | F | Sign player contracts | B C | 2 | 4 | 7 | #NAME? | Sign player contracts | D | #NAME? | D | 4 | #NAME? | #NAME? | 20.5615 | #NAME?
7 | G | Buy balls and trophies | D | 1 | 4 | 8 | #NAME? | Buy balls and trophies | E | #NAME? | E | 5 | #NAME? | #NAME? | 20.5703 | #NAME?
8 | H | Catering | E F | 0.5 | 1 | 3 | #NAME? | Catering | F | #NAME? | F | 6 | #NAME? | #NAME? | 20.5612 | #NAME?
9 | I | Prepare Location | E G | 2 | 3 | 5 | #NAME? | Prepare Location | G | #NAME? | G | 7 | #NAME? | #NAME? | 20.5615 | #NAME?
10 | J | Run tournament | H I | 2 | 2 | 3 | #NAME? | Run tournament | H | #NAME? | H | 8 | #NAME? | #NAME? | 20.5612 | #NAME?
[9 empty] | I | #NAME? | I | 9 | #NAME? | #NAME? | 20.5707 | #NAME?
[9 empty] | J | #NAME? | J | 10 | #NAME? | #NAME? | 20.571 | #NAME?
[11 empty] | none | 11 | #NAME? |  | 20.561
6% chance 23 days or more
on average
20.56 days