## Sheet1
simtable |  |  | Tennistourney.xlsx |  | Critical Activity: If activity takes .01 days longer | [5 empty] | 60 times we add .01 t olength of project |  |  | q11 would have 60(.01)/100
1 |  |  | Project Management.docx |  | does the project length increase |  |  | by .01days |  |  | 40 times we add 0 |  |  | added and then divided by .01
|  |  | Use RISKPERT to model duration of activity | [7 empty] | Probability D is critical |  |  | gets 60/100
run 100 iterations
|  | Activity | Predecessors | Min | Most Likely | Max | Duration |  |  |  | suppose 60 times Project takes .01
1 | A | Negotiate for location |  | 1 | 2 | 4 | 2.1767 | Negotiate for location |  |  | more days in Sim 4
2 | B | Contact seeded players |  | 5 | 8 | 12 | 8.1667 | Contact seeded players | Time |  |  | Activity | mean time +delta | Prob critical
3 | C | Plan promotion | A | 2 | 3 | 6 | 3.3333 | Plan promotion | A | 2.1767 | A | 1 | 20.5623 | 0.984 | 20.5708 | 1.8312
4 | D | Locate Officials | C | 1 | 2 | 5 | 2.3333 | Locate Officials | B | 8.1667 | B | 2 | 20.5526 | 0.016 | 20.5612 | 0.8752
5 | E | Send RSVPs | C | 6 | 10 | 12 | 9.6667 | Send RSVPs | C | 5.51 | C | 3 | 20.5623 | 0.984 | 20.5708 | 1.8312
6 | F | Sign player contracts | B C | 2 | 4 | 7 | 4.1667 | Sign player contracts | D | 7.8433 | D | 4 | 20.553 | 0.052985 | 20.5615 | 0.90406
7 | G | Buy balls and trophies | D | 1 | 4 | 8 | 4.1667 | Buy balls and trophies | E | 15.1767 | E | 5 | 20.5618 | 0.932 | 20.5703 | 1.7822
8 | H | Catering | E F | 0.5 | 1 | 3 | 1.25 | Catering | F | 12.3333 | F | 6 | 20.5526 | 0.016 | 20.5612 | 0.8752
9 | I | Prepare Location | E G | 2 | 3 | 5 | 3.1667 | Prepare Location | G | 12.01 | G | 7 | 20.553 | 0.052985 | 20.5615 | 0.90406
10 | J | Run tournament | H I | 2 | 2 | 3 | 2.1667 | Run tournament | H | 16.4267 | H | 8 | 20.5526 | 0.017796 | 20.5612 | 0.8782
11 | [8 empty] | I | 18.3433 | I | 9 | 20.5623 | 0.983 | 20.5707 | 1.8282
[9 empty] | J | 20.51 | J | 10 | 20.5625 | 1 | 20.571 | 1.8532
[11 empty] | none | 11 | 20.5525 |  | 20.561
6% chance 23 days or more
on average
20.56 days