## Sheet1
simtable
#NAME?
|  |  | Activity | Predecessors | Min | Max | Mean | Sigma | alpha | beta | rand | Duration
| 1 | A | Negotiate for location |  | 1 | 4 | 2 | 1 | 0.333 | 0.667 | 0.78654 | 3.0382 | Negotiate for location
| 2 | B | Contact seeded players |  | 5 | 12 | 8 | 3 | 0.142 | 0.19 | 0.29255 | 5.048 | Contact seeded players | Time
| 3 | C | Plan promotion | A | 2 | 6 | 4 | 1 | 1.5 | 1.5 | 0.50129 | 4.0041 | Plan promotion | A | 3.0382 | =Negotiate_for_location
| 4 | D | Locate Officials | C | 1 | 5 | 3 | 1 | 1.5 | 1.5 | 0.29171 | 2.333 | Locate Officials | B | 5.048 | =Contact_seeded_players
| 5 | E | Send RSVPs | C | 6 | 12 | 8 | 2 | 0.333 | 0.667 | 0.37042 | 6.5253 | Send RSVPs | C | 7.0423 | =A+Plan_promotion
| 6 | F | Sign player contracts | B C | 2 | 7 | 5 | 1 | 3 | 2 | 0.060105 | 3.3287 | Sign player contracts | D | 9.3753 | =C_+Locate_Officials
| 7 | G | Buy balls and trophies | D | 1 | 8 | 4 | 2 | 0.86 | 1.14 | 0.3438 | 2.8002 | Buy balls and trophies | E | 13.5675 | =C_+Send_RSVPs
| 8 | H | Catering | E F | 0.5 | 3 | 1 | 0.5 | 0.6 | 2.4 | 0.57996 | 0.94297 | Catering | F | 10.371 | =MAX(B,C_)+Sign_player_contracts
| 9 | I | Prepare Location | E G | 2 | 5 | 3 | 0.5 | 2.33 | 4.67 | 0.54325 | 3.0084 | Prepare Location | G | 12.1755 | =D+Buy_balls_and_trophies
| 10 | J | Run tournament | H I | 2 | 7 | 4 | 1 | 2 | 3 | 0.84935 | 5.1296 | Run tournament | H | 14.5105 | =MAX(E,F)+Catering
[14 empty] | I | 16.5759 | =MAX(E,G)+Prepare_Location
b | [13 empty] | J | 21.7055 | =MAX(H,I)+Run_tournament
[8 empty] | mean | #DIV/0!
[8 empty] | chance<=20 days | 0
A
B
C
D
E
F
G
H
I
J