## Sheet1
| simtable | [9 empty] | =BETA.INV(L6,J6,K6,F6,G6)
#NAME?
POLARIS MISSILE
|  |  | Activity | Predecessors | Min | Max | Mean | Sigma | alpha | beta | rand | Duration
| 1 | A | Negotiate for location |  | 1 | 4 | 2 | 1 | 0.333 | 0.667 | 0.42303 | 1.387 | Negotiate for location
| 2 | B | Contact seeded players |  | 5 | 12 | 8 | 3 | 0.142 | 0.19 | 0.28161 | 5.0367 | Contact seeded players | Time
| 3 | C | Plan promotion | A | 2 | 6 | 4 | 1 | 1.5 | 1.5 | 0.24748 | 3.1834 | Plan promotion | A | 1.387 | =Negotiate_for_location
| 4 | D | Locate Officials | C | 1 | 5 | 3 | 1 | 1.5 | 1.5 | 0.84338 | 4.1448 | Locate Officials | B | 5.0367 | =Contact_seeded_players
| 5 | E | Send RSVPs | C | 6 | 12 | 8 | 2 | 0.333 | 0.667 | 0.47737 | 7.096 | Send RSVPs | C | 4.5704 | =A+Plan_promotion
| 6 | F | Sign player contracts | B C | 2 | 7 | 5 | 1 | 3 | 2 | 0.065915 | 3.3741 | Sign player contracts | D | 8.7151 | =C_+Locate_Officials
| 7 | G | Buy balls and trophies | D | 1 | 8 | 4 | 2 | 0.86 | 1.14 | 0.9647 | 7.5718 | Buy balls and trophies | E | 11.6663 | =C_+Send_RSVPs
| 8 | H | Catering | E F | 0.5 | 3 | 1 | 0.5 | 0.6 | 2.4 | 0.86635 | 1.6183 | Catering | F | 8.4109 | =MAX(B,C_)+Sign_player_contracts
| 9 | I | Prepare Location | E G | 2 | 5 | 3 | 0.5 | 2.33 | 4.67 | 0.19917 | 2.5394 | Prepare Location | G | 16.2869 | =D+Buy_balls_and_trophies
| 10 | J | Run tournament | H I | 2 | 7 | 4 | 1 | 2 | 3 | 0.34635 | 3.4945 | Run tournament | H | 13.2846 | =MAX(E,F)+Catering
[14 empty] | I | 18.8263 | =MAX(E,G)+Prepare_Location
b | [13 empty] | J | 22.3208 | =MAX(H,I)+Run_tournament
[8 empty] | mean | 22.2317
[5 empty] | 22.3208 |  |  | chance<=20 weeks | 0.175
|  |  |  | 1 | 21.3712
|  |  |  | 2 | 17.2456
|  |  |  | 3 | 18.5998
|  |  |  | 4 | 16.2036
|  |  |  | 5 | 22.5488
|  |  |  | 6 | 22.6289
|  |  |  | 7 | 22.599
|  |  |  | 8 | 22.8998
|  |  |  | 9 | 19.9705
|  |  |  | 10 | 26.3838
|  |  |  | 11 | 26.1956
|  |  |  | 12 | 20.2299
|  |  |  | 13 | 22.5933
|  |  |  | 14 | 24.4668
|  |  |  | 15 | 22.3877
|  |  |  | 16 | 16.9356
|  |  |  | 17 | 22.3606
|  |  |  | 18 | 24.0863
|  |  |  | 19 | 19.6104
|  |  |  | 20 | 21.3734
|  |  |  | 21 | 29.0976
|  |  |  | 22 | 22.7496
|  |  |  | 23 | 23.8817
|  |  |  | 24 | 21.9925
|  |  |  | 25 | 19.4449
|  |  |  | 26 | 21.9903
|  |  |  | 27 | 22.8561
|  |  |  | 28 | 20.0467
|  |  |  | 29 | 16.771
|  |  |  | 30 | 18.0417
|  |  |  | 31 | 23.8978
|  |  |  | 32 | 28.6702
|  |  |  | 33 | 21.3691
|  |  |  | 34 | 23.2744
|  |  |  | 35 | 20.2322
|  |  |  | 36 | 19.9964
|  |  |  | 37 | 22.7389
|  |  |  | 38 | 19.0859
|  |  |  | 39 | 26.7406
|  |  |  | 40 | 24.4148
|  |  |  | 41 | 22.2307
|  |  |  | 42 | 24.1704
|  |  |  | 43 | 22.4941
|  |  |  | 44 | 17.1116
|  |  |  | 45 | 19.6625
|  |  |  | 46 | 22.9747
|  |  |  | 47 | 23.0596
|  |  |  | 48 | 19.9408
|  |  |  | 49 | 17.7927
|  |  |  | 50 | 22.282
|  |  |  | 51 | 22.3033
|  |  |  | 52 | 21.6542
|  |  |  | 53 | 25.4883
|  |  |  | 54 | 20.7581
|  |  |  | 55 | 21.8959
|  |  |  | 56 | 21.3419
|  |  |  | 57 | 22.1089
|  |  |  | 58 | 24.3243
|  |  |  | 59 | 27.5461
|  |  |  | 60 | 24.4475
|  |  |  | 61 | 23.1016
|  |  |  | 62 | 23.3405
|  |  |  | 63 | 16.9961
|  |  |  | 64 | 24.3476
|  |  |  | 65 | 23.1547
|  |  |  | 66 | 22.5903
|  |  |  | 67 | 24.467
|  |  |  | 68 | 27.1403
|  |  |  | 69 | 20.6727
|  |  |  | 70 | 23.1087
|  |  |  | 71 | 21.5358
|  |  |  | 72 | 23.5842
|  |  |  | 73 | 27.8681
|  |  |  | 74 | 20.5397
|  |  |  | 75 | 23.0387
|  |  |  | 76 | 18.9126
|  |  |  | 77 | 22.8687
|  |  |  | 78 | 27.0371
|  |  |  | 79 | 18.9933
|  |  |  | 80 | 24.4708
|  |  |  | 81 | 26.4225
|  |  |  | 82 | 22.7286
|  |  |  | 83 | 23.6646
|  |  |  | 84 | 21.126
|  |  |  | 85 | 22.5506
|  |  |  | 86 | 21.3818
|  |  |  | 87 | 23.1859
|  |  |  | 88 | 19.934
|  |  |  | 89 | 20.596
|  |  |  | 90 | 22.7177
|  |  |  | 91 | 22.0338
|  |  |  | 92 | 22.4895
|  |  |  | 93 | 22.9055
|  |  |  | 94 | 19.9707
|  |  |  | 95 | 22.1919
|  |  |  | 96 | 24.0408
|  |  |  | 97 | 20.4171
|  |  |  | 98 | 23.6858
|  |  |  | 99 | 23.5158
|  |  |  | 100 | 21.674
|  |  |  | 101 | 21.9123
|  |  |  | 102 | 21.5961
|  |  |  | 103 | 19.4616
|  |  |  | 104 | 22.1073
|  |  |  | 105 | 23.87
|  |  |  | 106 | 21.7042
|  |  |  | 107 | 24.116
|  |  |  | 108 | 18.949
|  |  |  | 109 | 27.7638
|  |  |  | 110 | 21.4002
|  |  |  | 111 | 19.8223
|  |  |  | 112 | 21.6307
|  |  |  | 113 | 20.0791
|  |  |  | 114 | 18.1946
|  |  |  | 115 | 19.792
|  |  |  | 116 | 21.6529
|  |  |  | 117 | 20.9122
|  |  |  | 118 | 22.6789
|  |  |  | 119 | 21.815
|  |  |  | 120 | 24.1053
|  |  |  | 121 | 22.4266
|  |  |  | 122 | 19.6034
|  |  |  | 123 | 18.9831
|  |  |  | 124 | 23.6083
|  |  |  | 125 | 23.7501
|  |  |  | 126 | 18.8071
|  |  |  | 127 | 23.1558
|  |  |  | 128 | 19.621
|  |  |  | 129 | 20.5437
|  |  |  | 130 | 22.1907
|  |  |  | 131 | 23.5064
|  |  |  | 132 | 25.9949
|  |  |  | 133 | 21.0912
|  |  |  | 134 | 20.51
|  |  |  | 135 | 16.9935
|  |  |  | 136 | 17.2131
|  |  |  | 137 | 24.634
|  |  |  | 138 | 25.3767
|  |  |  | 139 | 26.0979
|  |  |  | 140 | 19.9639
|  |  |  | 141 | 22.8629
|  |  |  | 142 | 22.9816
|  |  |  | 143 | 20.706
|  |  |  | 144 | 20.428
|  |  |  | 145 | 21.3885
|  |  |  | 146 | 23.3545
|  |  |  | 147 | 21.1958
|  |  |  | 148 | 21.8028
|  |  |  | 149 | 22.7907
|  |  |  | 150 | 21.0107
|  |  |  | 151 | 19.8961
|  |  |  | 152 | 21.77
|  |  |  | 153 | 20.7401
|  |  |  | 154 | 22.3832
|  |  |  | 155 | 24.2125
|  |  |  | 156 | 20.1971
|  |  |  | 157 | 21.9851
|  |  |  | 158 | 20.1848
|  |  |  | 159 | 27.9515
|  |  |  | 160 | 21.3037
|  |  |  | 161 | 19.0497
|  |  |  | 162 | 24.6875
|  |  |  | 163 | 16.3399
|  |  |  | 164 | 20.1779
|  |  |  | 165 | 23.0871
|  |  |  | 166 | 16.6624
|  |  |  | 167 | 23.0003
|  |  |  | 168 | 24.7989
|  |  |  | 169 | 20.0171
|  |  |  | 170 | 18.8944
|  |  |  | 171 | 20.8258
|  |  |  | 172 | 18.3984
|  |  |  | 173 | 20.357
|  |  |  | 174 | 21.5348
|  |  |  | 175 | 20.4675
|  |  |  | 176 | 19.0429
|  |  |  | 177 | 22.0813
|  |  |  | 178 | 23.1968
|  |  |  | 179 | 23.3513
|  |  |  | 180 | 23.5366
|  |  |  | 181 | 20.8844
|  |  |  | 182 | 23.9217
|  |  |  | 183 | 21.038
|  |  |  | 184 | 24.4012
|  |  |  | 185 | 21.7603
|  |  |  | 186 | 23.1383
|  |  |  | 187 | 25.3217
|  |  |  | 188 | 20.4269
|  |  |  | 189 | 26.0724
|  |  |  | 190 | 21.2197
|  |  |  | 191 | 27.0439
|  |  |  | 192 | 20.8321
|  |  |  | 193 | 19.8744
|  |  |  | 194 | 24.6007
|  |  |  | 195 | 22.3412
|  |  |  | 196 | 21.9339
|  |  |  | 197 | 23.1138
|  |  |  | 198 | 21.9078
|  |  |  | 199 | 17.5946
|  |  |  | 200 | 23.0963
|  |  |  | 201 | 21.6683
|  |  |  | 202 | 18.5326
|  |  |  | 203 | 19.4978
|  |  |  | 204 | 17.5629
|  |  |  | 205 | 24.0418
|  |  |  | 206 | 23.7212
|  |  |  | 207 | 26.2843
|  |  |  | 208 | 20.919
|  |  |  | 209 | 21.3695
|  |  |  | 210 | 22.5862
|  |  |  | 211 | 20.3899
|  |  |  | 212 | 18.7178
|  |  |  | 213 | 29.2121
|  |  |  | 214 | 21.7924
|  |  |  | 215 | 20.8544
|  |  |  | 216 | 23.0963
|  |  |  | 217 | 25.2064
|  |  |  | 218 | 16.2658
|  |  |  | 219 | 21.0317
|  |  |  | 220 | 25.2046
|  |  |  | 221 | 21.4143
|  |  |  | 222 | 23.4306
|  |  |  | 223 | 21.8013
|  |  |  | 224 | 22.5484
|  |  |  | 225 | 21.1004
|  |  |  | 226 | 27.1931
|  |  |  | 227 | 22.4723
|  |  |  | 228 | 22.2418
|  |  |  | 229 | 22.5159
|  |  |  | 230 | 20.3322
|  |  |  | 231 | 18.1484
|  |  |  | 232 | 24.2026
|  |  |  | 233 | 25.1087
|  |  |  | 234 | 25.0685
|  |  |  | 235 | 24.2898
|  |  |  | 236 | 18.1961
|  |  |  | 237 | 25.1997
|  |  |  | 238 | 23.384
|  |  |  | 239 | 20.6135
|  |  |  | 240 | 17.6779
|  |  |  | 241 | 23.3461
|  |  |  | 242 | 22.8134
|  |  |  | 243 | 21.1981
|  |  |  | 244 | 22.8932
|  |  |  | 245 | 22.1885
|  |  |  | 246 | 26.7739
|  |  |  | 247 | 21.3032
|  |  |  | 248 | 18.2272
|  |  |  | 249 | 16.5647
|  |  |  | 250 | 27.1421
|  |  |  | 251 | 20.8286
|  |  |  | 252 | 21.106
|  |  |  | 253 | 25.262
|  |  |  | 254 | 20.3186
|  |  |  | 255 | 23.9292
|  |  |  | 256 | 22.3749
|  |  |  | 257 | 19.9636
|  |  |  | 258 | 20.8357
|  |  |  | 259 | 18.1031
|  |  |  | 260 | 22.9072
|  |  |  | 261 | 21.2043
|  |  |  | 262 | 24.4752
|  |  |  | 263 | 19.8837
|  |  |  | 264 | 21.2224
|  |  |  | 265 | 25.2049
|  |  |  | 266 | 23.0883
|  |  |  | 267 | 16.7542
|  |  |  | 268 | 26.4754
|  |  |  | 269 | 21.0145
|  |  |  | 270 | 24.1293
|  |  |  | 271 | 19.8123
|  |  |  | 272 | 22.5394
|  |  |  | 273 | 21.8371
|  |  |  | 274 | 21.0254
|  |  |  | 275 | 24.1922
|  |  |  | 276 | 22.8231
|  |  |  | 277 | 19.0569
|  |  |  | 278 | 21.9561
|  |  |  | 279 | 22.5476
|  |  |  | 280 | 20.007
|  |  |  | 281 | 24.5776
|  |  |  | 282 | 18.6692
|  |  |  | 283 | 20.7424
|  |  |  | 284 | 22.6601
|  |  |  | 285 | 25.1234
|  |  |  | 286 | 24.8032
|  |  |  | 287 | 23.8784
|  |  |  | 288 | 26.7475
|  |  |  | 289 | 21.885
|  |  |  | 290 | 26.5315
|  |  |  | 291 | 21.1492
|  |  |  | 292 | 21.399
|  |  |  | 293 | 21.7204
|  |  |  | 294 | 20.9065
|  |  |  | 295 | 16.1923
|  |  |  | 296 | 21.0845
|  |  |  | 297 | 20.0429
|  |  |  | 298 | 27.6066
|  |  |  | 299 | 22.2464
|  |  |  | 300 | 22.9503
|  |  |  | 301 | 19.9557
|  |  |  | 302 | 20.769
|  |  |  | 303 | 23.2017
|  |  |  | 304 | 24.6037
|  |  |  | 305 | 24.4372
|  |  |  | 306 | 23.9517
|  |  |  | 307 | 18.7962
|  |  |  | 308 | 25.2271
|  |  |  | 309 | 24.4161
|  |  |  | 310 | 20.9787
|  |  |  | 311 | 21.8964
|  |  |  | 312 | 21.7637
|  |  |  | 313 | 28.211
|  |  |  | 314 | 23.8143
|  |  |  | 315 | 23.0965
|  |  |  | 316 | 23.3891
|  |  |  | 317 | 20.3649
|  |  |  | 318 | 23.898
|  |  |  | 319 | 20.0764
|  |  |  | 320 | 21.2235
|  |  |  | 321 | 21.0185
|  |  |  | 322 | 23.6891
|  |  |  | 323 | 21.7518
|  |  |  | 324 | 24.3396
|  |  |  | 325 | 23.0073
|  |  |  | 326 | 17.4519
|  |  |  | 327 | 22.1257
|  |  |  | 328 | 22.2994
|  |  |  | 329 | 24.8611
|  |  |  | 330 | 19.4655
|  |  |  | 331 | 21.8753
|  |  |  | 332 | 24.1204
|  |  |  | 333 | 22.9428
|  |  |  | 334 | 26.684
|  |  |  | 335 | 18.8795
|  |  |  | 336 | 22.7988
|  |  |  | 337 | 21.1066
|  |  |  | 338 | 24.3671
|  |  |  | 339 | 22.8407
|  |  |  | 340 | 19.6696
|  |  |  | 341 | 16.6146
|  |  |  | 342 | 22.3372
|  |  |  | 343 | 21.2085
|  |  |  | 344 | 21.5435
|  |  |  | 345 | 18.718
|  |  |  | 346 | 18.302
|  |  |  | 347 | 26.1752
|  |  |  | 348 | 22.744
|  |  |  | 349 | 21.3662
|  |  |  | 350 | 22.629
|  |  |  | 351 | 25.8631
|  |  |  | 352 | 21.9751
|  |  |  | 353 | 20.2157
|  |  |  | 354 | 20.3454
|  |  |  | 355 | 23.585
|  |  |  | 356 | 25.4121
|  |  |  | 357 | 20.9105
|  |  |  | 358 | 24.2344
|  |  |  | 359 | 24.9792
|  |  |  | 360 | 24.2083
|  |  |  | 361 | 22.5316
|  |  |  | 362 | 25.0746
|  |  |  | 363 | 24.1604
|  |  |  | 364 | 23.0082
|  |  |  | 365 | 21.2872
|  |  |  | 366 | 24.9185
|  |  |  | 367 | 19.1141
|  |  |  | 368 | 24.0594
|  |  |  | 369 | 21.8445
|  |  |  | 370 | 20.0941
|  |  |  | 371 | 22.5648
|  |  |  | 372 | 21.9953
|  |  |  | 373 | 20.0126
|  |  |  | 374 | 24.7855
|  |  |  | 375 | 26.2857
|  |  |  | 376 | 24.4554
|  |  |  | 377 | 24.729
|  |  |  | 378 | 21.9462
|  |  |  | 379 | 21.1746
|  |  |  | 380 | 20.1095
|  |  |  | 381 | 22.6991
|  |  |  | 382 | 18.2828
|  |  |  | 383 | 21.3171
|  |  |  | 384 | 18.5
|  |  |  | 385 | 19.9195
|  |  |  | 386 | 22.8458
|  |  |  | 387 | 22.932
|  |  |  | 388 | 24.2918
|  |  |  | 389 | 23.5542
|  |  |  | 390 | 19.4917
|  |  |  | 391 | 18.7568
|  |  |  | 392 | 26.3772
|  |  |  | 393 | 24.2076
|  |  |  | 394 | 20.1339
|  |  |  | 395 | 19.0967
|  |  |  | 396 | 24.2637
|  |  |  | 397 | 18.9688
|  |  |  | 398 | 22.7942
|  |  |  | 399 | 22.9122
|  |  |  | 400 | 22.5249
|  |  |  | 401 | 19.4505
|  |  |  | 402 | 21.3279
|  |  |  | 403 | 27.6062
|  |  |  | 404 | 23.9153
|  |  |  | 405 | 22.5153
|  |  |  | 406 | 22.518
|  |  |  | 407 | 19.8808
|  |  |  | 408 | 23.6285
|  |  |  | 409 | 18.8501
|  |  |  | 410 | 23.8222
|  |  |  | 411 | 22.5055
|  |  |  | 412 | 21.2931
|  |  |  | 413 | 23.6063
|  |  |  | 414 | 23.0872
|  |  |  | 415 | 19.5372
|  |  |  | 416 | 23.1561
|  |  |  | 417 | 22.5212
|  |  |  | 418 | 25.1022
|  |  |  | 419 | 21.4285
|  |  |  | 420 | 23.194
|  |  |  | 421 | 26.0742
|  |  |  | 422 | 20.9233
|  |  |  | 423 | 23.9694
|  |  |  | 424 | 23.7269
|  |  |  | 425 | 25.7128
|  |  |  | 426 | 22.3731
|  |  |  | 427 | 23.2171
|  |  |  | 428 | 24.7064
|  |  |  | 429 | 17.7871
|  |  |  | 430 | 23.2312
|  |  |  | 431 | 21.3862
|  |  |  | 432 | 18.6584
|  |  |  | 433 | 26.0371
|  |  |  | 434 | 23.0801
|  |  |  | 435 | 23.1802
|  |  |  | 436 | 20.9425
|  |  |  | 437 | 20.5338
|  |  |  | 438 | 24.5212
|  |  |  | 439 | 23.4172
|  |  |  | 440 | 19.73
|  |  |  | 441 | 24.9762
|  |  |  | 442 | 22.5399
|  |  |  | 443 | 19.5274
|  |  |  | 444 | 23.0301
|  |  |  | 445 | 22.5795
|  |  |  | 446 | 23.2372
|  |  |  | 447 | 17.7021
|  |  |  | 448 | 18.5394
|  |  |  | 449 | 21.0124
|  |  |  | 450 | 24.9487
|  |  |  | 451 | 27.9264
|  |  |  | 452 | 18.6997
|  |  |  | 453 | 23.132
|  |  |  | 454 | 22.6649
|  |  |  | 455 | 20.1224
|  |  |  | 456 | 22.5584
|  |  |  | 457 | 25.2745
|  |  |  | 458 | 24.7375
|  |  |  | 459 | 23.4463
|  |  |  | 460 | 23.174
|  |  |  | 461 | 19.1592
|  |  |  | 462 | 24.6877
|  |  |  | 463 | 21.9735
|  |  |  | 464 | 24.1959
|  |  |  | 465 | 22.3541
|  |  |  | 466 | 19.0277
|  |  |  | 467 | 22.2229
|  |  |  | 468 | 21.7461
|  |  |  | 469 | 21.6217
|  |  |  | 470 | 22.8561
|  |  |  | 471 | 21.1964
|  |  |  | 472 | 24.605
|  |  |  | 473 | 29.2307
|  |  |  | 474 | 19.2701
|  |  |  | 475 | 19.2826
|  |  |  | 476 | 23.4319
|  |  |  | 477 | 21.7959
|  |  |  | 478 | 21.6429
|  |  |  | 479 | 25.2425
|  |  |  | 480 | 24.5458
|  |  |  | 481 | 20.4274
|  |  |  | 482 | 20.4664
|  |  |  | 483 | 21.0208
|  |  |  | 484 | 22.4784
|  |  |  | 485 | 24.2299
|  |  |  | 486 | 19.955
|  |  |  | 487 | 24.5111
|  |  |  | 488 | 22.3258
|  |  |  | 489 | 24.7425
|  |  |  | 490 | 22.9881
|  |  |  | 491 | 23.3655
|  |  |  | 492 | 20.2514
|  |  |  | 493 | 23.4296
|  |  |  | 494 | 20.7837
|  |  |  | 495 | 20.0977
|  |  |  | 496 | 23.1851
|  |  |  | 497 | 24.6976
|  |  |  | 498 | 21.425
|  |  |  | 499 | 16.9216
|  |  |  | 500 | 21.613
|  |  |  | 501 | 20.9761
|  |  |  | 502 | 22.2313
|  |  |  | 503 | 23.1288
|  |  |  | 504 | 21.9295
|  |  |  | 505 | 24.7696
|  |  |  | 506 | 18.3464
|  |  |  | 507 | 23.717
|  |  |  | 508 | 18.8796
|  |  |  | 509 | 21.6763
|  |  |  | 510 | 24.3665
|  |  |  | 511 | 18.925
|  |  |  | 512 | 19.3652
|  |  |  | 513 | 22.4996
|  |  |  | 514 | 20.2955
|  |  |  | 515 | 19.1027
|  |  |  | 516 | 23.0164
|  |  |  | 517 | 20.0588
|  |  |  | 518 | 23.2855
|  |  |  | 519 | 23.9353
|  |  |  | 520 | 23.8402
|  |  |  | 521 | 17.9467
|  |  |  | 522 | 22.3422
|  |  |  | 523 | 22.7434
|  |  |  | 524 | 25.1634
|  |  |  | 525 | 20.5476
|  |  |  | 526 | 19.296
|  |  |  | 527 | 21.4758
|  |  |  | 528 | 25.2219
|  |  |  | 529 | 23.8373
|  |  |  | 530 | 22.1677
|  |  |  | 531 | 21.5316
|  |  |  | 532 | 22.5015
|  |  |  | 533 | 22.2947
|  |  |  | 534 | 20.4487
|  |  |  | 535 | 19.7017
|  |  |  | 536 | 23.6343
|  |  |  | 537 | 20.0396
|  |  |  | 538 | 22.8927
|  |  |  | 539 | 20.8091
|  |  |  | 540 | 23.9247
|  |  |  | 541 | 19.2459
|  |  |  | 542 | 23.0391
|  |  |  | 543 | 22.1581
|  |  |  | 544 | 24.7528
|  |  |  | 545 | 21.3896
|  |  |  | 546 | 21.862
|  |  |  | 547 | 23.76
|  |  |  | 548 | 22.6024
|  |  |  | 549 | 20.8501
|  |  |  | 550 | 25.4325
|  |  |  | 551 | 24.4638
|  |  |  | 552 | 24.0304
|  |  |  | 553 | 21.6949
|  |  |  | 554 | 22.7065
|  |  |  | 555 | 18.6543
|  |  |  | 556 | 25.1189
|  |  |  | 557 | 25.7178
|  |  |  | 558 | 23.9351
|  |  |  | 559 | 17.4507
|  |  |  | 560 | 20.8163
|  |  |  | 561 | 25.4636
|  |  |  | 562 | 17.6329
|  |  |  | 563 | 22.6752
|  |  |  | 564 | 20.9583
|  |  |  | 565 | 25.2771
|  |  |  | 566 | 24.3229
|  |  |  | 567 | 26.4277
|  |  |  | 568 | 18.9927
|  |  |  | 569 | 24.8215
|  |  |  | 570 | 20.9042
|  |  |  | 571 | 20.8629
|  |  |  | 572 | 22.2397
|  |  |  | 573 | 21.6261
|  |  |  | 574 | 25.4421
|  |  |  | 575 | 20.932
|  |  |  | 576 | 22.585
|  |  |  | 577 | 22.9207
|  |  |  | 578 | 20.5311
|  |  |  | 579 | 24.0869
|  |  |  | 580 | 21.2431
|  |  |  | 581 | 23.1755
|  |  |  | 582 | 19.6604
|  |  |  | 583 | 23.4718
|  |  |  | 584 | 21.8105
|  |  |  | 585 | 24.6757
|  |  |  | 586 | 20.8374
|  |  |  | 587 | 22.8256
|  |  |  | 588 | 24.9939
|  |  |  | 589 | 20.0425
|  |  |  | 590 | 20.7969
|  |  |  | 591 | 23.8153
|  |  |  | 592 | 23.9615
|  |  |  | 593 | 21.1037
|  |  |  | 594 | 24.1686
|  |  |  | 595 | 24.3233
|  |  |  | 596 | 24.2463
|  |  |  | 597 | 23.1555
|  |  |  | 598 | 23.1382
|  |  |  | 599 | 19.2385
|  |  |  | 600 | 18.1849
|  |  |  | 601 | 23.963
|  |  |  | 602 | 23.0138
|  |  |  | 603 | 23.0329
|  |  |  | 604 | 24.9504
|  |  |  | 605 | 22.6443
|  |  |  | 606 | 22.1351
|  |  |  | 607 | 23.1526
|  |  |  | 608 | 23.1385
|  |  |  | 609 | 23.754
|  |  |  | 610 | 25.5579
|  |  |  | 611 | 22.279
|  |  |  | 612 | 21.7075
|  |  |  | 613 | 23.8434
|  |  |  | 614 | 25.3945
|  |  |  | 615 | 20.8759
|  |  |  | 616 | 21.4953
|  |  |  | 617 | 21.8433
|  |  |  | 618 | 25.0872
|  |  |  | 619 | 22.7552
|  |  |  | 620 | 25.3563
|  |  |  | 621 | 23.0319
|  |  |  | 622 | 22.9988
|  |  |  | 623 | 22.1884
|  |  |  | 624 | 22.6455
|  |  |  | 625 | 24.5985
|  |  |  | 626 | 26.7758
|  |  |  | 627 | 21.5765
|  |  |  | 628 | 27.1225
|  |  |  | 629 | 21.5991
|  |  |  | 630 | 19.5455
|  |  |  | 631 | 21.919
|  |  |  | 632 | 18.1797
|  |  |  | 633 | 21.8371
|  |  |  | 634 | 19.7429
|  |  |  | 635 | 19.9845
|  |  |  | 636 | 21.5886
|  |  |  | 637 | 24.6926
|  |  |  | 638 | 23.6634
|  |  |  | 639 | 19.6954
|  |  |  | 640 | 22.972
|  |  |  | 641 | 22.8089
|  |  |  | 642 | 23.5829
|  |  |  | 643 | 19.6426
|  |  |  | 644 | 24.9574
|  |  |  | 645 | 23.3804
|  |  |  | 646 | 26.6616
|  |  |  | 647 | 21.5691
|  |  |  | 648 | 23.4527
|  |  |  | 649 | 23.3818
|  |  |  | 650 | 16.9182
|  |  |  | 651 | 22.3413
|  |  |  | 652 | 20.1616
|  |  |  | 653 | 20.9617
|  |  |  | 654 | 18.5134
|  |  |  | 655 | 23.6147
|  |  |  | 656 | 21.0358
|  |  |  | 657 | 21.877
|  |  |  | 658 | 19.7802
|  |  |  | 659 | 25.5417
|  |  |  | 660 | 22.7888
|  |  |  | 661 | 22.861
|  |  |  | 662 | 17.9757
|  |  |  | 663 | 25.0005
|  |  |  | 664 | 23.1228
|  |  |  | 665 | 19.0757
|  |  |  | 666 | 25.0071
|  |  |  | 667 | 27.1236
|  |  |  | 668 | 23.2423
|  |  |  | 669 | 24.8868
|  |  |  | 670 | 23.6042
|  |  |  | 671 | 17.6951
|  |  |  | 672 | 23.7621
|  |  |  | 673 | 16.7625
|  |  |  | 674 | 22.2764
|  |  |  | 675 | 19.1086
|  |  |  | 676 | 19.5287
|  |  |  | 677 | 18.0183
|  |  |  | 678 | 21.1115
|  |  |  | 679 | 20.5476
|  |  |  | 680 | 22.9115
|  |  |  | 681 | 19.5098
|  |  |  | 682 | 25.9085
|  |  |  | 683 | 21.8467
|  |  |  | 684 | 19.2148
|  |  |  | 685 | 23.9165
|  |  |  | 686 | 22.5682
|  |  |  | 687 | 21.4861
|  |  |  | 688 | 21.6136
|  |  |  | 689 | 17.8761
|  |  |  | 690 | 20.2857
|  |  |  | 691 | 17.2922
|  |  |  | 692 | 22.658
|  |  |  | 693 | 24.4536
|  |  |  | 694 | 21.3061
|  |  |  | 695 | 20.5637
|  |  |  | 696 | 24.9779
|  |  |  | 697 | 18.1713
|  |  |  | 698 | 23.7524
|  |  |  | 699 | 22.8499
|  |  |  | 700 | 20.9881
|  |  |  | 701 | 24.0626
|  |  |  | 702 | 23.368
|  |  |  | 703 | 22.6841
|  |  |  | 704 | 18.5834
|  |  |  | 705 | 28.9353
|  |  |  | 706 | 24.3279
|  |  |  | 707 | 21.5556
|  |  |  | 708 | 21.8099
|  |  |  | 709 | 19.5165
|  |  |  | 710 | 22.5719
|  |  |  | 711 | 25.1803
|  |  |  | 712 | 20.7083
|  |  |  | 713 | 22.5264
|  |  |  | 714 | 24.6709
|  |  |  | 715 | 23.2045
|  |  |  | 716 | 23.5826
|  |  |  | 717 | 23.0294
|  |  |  | 718 | 18.5687
|  |  |  | 719 | 21.2881
|  |  |  | 720 | 25.891
|  |  |  | 721 | 22.3839
|  |  |  | 722 | 17.7022
|  |  |  | 723 | 24.0463
|  |  |  | 724 | 26.7147
|  |  |  | 725 | 27.5107
|  |  |  | 726 | 23.3208
|  |  |  | 727 | 24.9727
|  |  |  | 728 | 24.4068
|  |  |  | 729 | 25.2303
|  |  |  | 730 | 23.6364
|  |  |  | 731 | 21.9331
|  |  |  | 732 | 21.8972
|  |  |  | 733 | 22.3065
|  |  |  | 734 | 19.1094
|  |  |  | 735 | 21.9206
|  |  |  | 736 | 22.6777
|  |  |  | 737 | 24.6296
|  |  |  | 738 | 21.126
|  |  |  | 739 | 24.6146
|  |  |  | 740 | 19.6824
|  |  |  | 741 | 23.7187
|  |  |  | 742 | 22.0581
|  |  |  | 743 | 24.0006
|  |  |  | 744 | 25.3594
|  |  |  | 745 | 20.8736
|  |  |  | 746 | 20.4384
|  |  |  | 747 | 21.1069
|  |  |  | 748 | 20.8191
|  |  |  | 749 | 19.4012
|  |  |  | 750 | 24.8489
|  |  |  | 751 | 25.4735
|  |  |  | 752 | 21.5603
|  |  |  | 753 | 20.7055
|  |  |  | 754 | 22.6774
|  |  |  | 755 | 22.3164
|  |  |  | 756 | 23.4351
|  |  |  | 757 | 21.4698
|  |  |  | 758 | 23.1205
|  |  |  | 759 | 22.5953
|  |  |  | 760 | 22.718
|  |  |  | 761 | 20.5066
|  |  |  | 762 | 19.6302
|  |  |  | 763 | 25.5079
|  |  |  | 764 | 26.4443
|  |  |  | 765 | 20.0255
|  |  |  | 766 | 22.1478
|  |  |  | 767 | 21.9155
|  |  |  | 768 | 22.1122
|  |  |  | 769 | 27.1053
|  |  |  | 770 | 20.9814
|  |  |  | 771 | 20.3505
|  |  |  | 772 | 19.035
|  |  |  | 773 | 22.0363
|  |  |  | 774 | 18.4151
|  |  |  | 775 | 21.1562
|  |  |  | 776 | 20.3251
|  |  |  | 777 | 26.1487
|  |  |  | 778 | 24.2835
|  |  |  | 779 | 24.4304
|  |  |  | 780 | 24.5302
|  |  |  | 781 | 23.6208
|  |  |  | 782 | 21.4331
|  |  |  | 783 | 21.4186
|  |  |  | 784 | 26.0469
|  |  |  | 785 | 22.9287
|  |  |  | 786 | 22.8698
|  |  |  | 787 | 18.4921
|  |  |  | 788 | 20.3633
|  |  |  | 789 | 20.7335
|  |  |  | 790 | 20.7834
|  |  |  | 791 | 20.2045
|  |  |  | 792 | 20.1545
|  |  |  | 793 | 25.5072
|  |  |  | 794 | 19.4952
|  |  |  | 795 | 22.9481
|  |  |  | 796 | 20.5183
|  |  |  | 797 | 20.1299
|  |  |  | 798 | 23.7536
|  |  |  | 799 | 21.004
|  |  |  | 800 | 22.3831
|  |  |  | 801 | 20.9334
|  |  |  | 802 | 21.3303
|  |  |  | 803 | 24.6258
|  |  |  | 804 | 21.0912
|  |  |  | 805 | 21.8083
|  |  |  | 806 | 23.6275
|  |  |  | 807 | 20.4224
|  |  |  | 808 | 24.9417
|  |  |  | 809 | 21.136
|  |  |  | 810 | 23.8809
|  |  |  | 811 | 24.0571
|  |  |  | 812 | 24.2569
|  |  |  | 813 | 18.2871
|  |  |  | 814 | 23.7297
|  |  |  | 815 | 22.231
|  |  |  | 816 | 23.0704
|  |  |  | 817 | 27.4156
|  |  |  | 818 | 23.6961
|  |  |  | 819 | 22.7216
|  |  |  | 820 | 25.5984
|  |  |  | 821 | 22.143
|  |  |  | 822 | 21.9072
|  |  |  | 823 | 20.533
|  |  |  | 824 | 26.7402
|  |  |  | 825 | 22.0996
|  |  |  | 826 | 25.1729
|  |  |  | 827 | 25.6424
|  |  |  | 828 | 21.4935
|  |  |  | 829 | 23.7337
|  |  |  | 830 | 25.2835
|  |  |  | 831 | 25.2673
|  |  |  | 832 | 23.9434
|  |  |  | 833 | 21.5614
|  |  |  | 834 | 20.1188
|  |  |  | 835 | 25.6841
|  |  |  | 836 | 21.1091
|  |  |  | 837 | 22.2839
|  |  |  | 838 | 18.8823
|  |  |  | 839 | 22.4332
|  |  |  | 840 | 24.8924
|  |  |  | 841 | 21.9075
|  |  |  | 842 | 19.4498
|  |  |  | 843 | 22.2699
|  |  |  | 844 | 20.5954
|  |  |  | 845 | 19.8925
|  |  |  | 846 | 26.7745
|  |  |  | 847 | 20.7576
|  |  |  | 848 | 20.2523
|  |  |  | 849 | 21.9166
|  |  |  | 850 | 21.3607
|  |  |  | 851 | 25.3232
|  |  |  | 852 | 22.3782
|  |  |  | 853 | 24.3448
|  |  |  | 854 | 21.2649
|  |  |  | 855 | 22.4096
|  |  |  | 856 | 20.565
|  |  |  | 857 | 20.8208
|  |  |  | 858 | 21.5651
|  |  |  | 859 | 18.409
|  |  |  | 860 | 18.7981
|  |  |  | 861 | 24.7151
|  |  |  | 862 | 24.7184
|  |  |  | 863 | 22.7531
|  |  |  | 864 | 23.8492
|  |  |  | 865 | 21.8056
|  |  |  | 866 | 24.5774
|  |  |  | 867 | 21.2651
|  |  |  | 868 | 22.5054
|  |  |  | 869 | 24.2172
|  |  |  | 870 | 21.0304
|  |  |  | 871 | 25.0363
|  |  |  | 872 | 25.433
|  |  |  | 873 | 16.7861
|  |  |  | 874 | 22.339
|  |  |  | 875 | 18.1409
|  |  |  | 876 | 21.188
|  |  |  | 877 | 20.2193
|  |  |  | 878 | 19.0794
|  |  |  | 879 | 27.172
|  |  |  | 880 | 24.083
|  |  |  | 881 | 24.3429
|  |  |  | 882 | 23.3469
|  |  |  | 883 | 23.611
|  |  |  | 884 | 24.2999
|  |  |  | 885 | 28.37
|  |  |  | 886 | 17.341
|  |  |  | 887 | 20.7893
|  |  |  | 888 | 21.9426
|  |  |  | 889 | 23.8138
|  |  |  | 890 | 22.6866
|  |  |  | 891 | 21.8493
|  |  |  | 892 | 22.595
|  |  |  | 893 | 23.8737
|  |  |  | 894 | 24.8576
|  |  |  | 895 | 23.9065
|  |  |  | 896 | 23.6753
|  |  |  | 897 | 20.7174
|  |  |  | 898 | 19.3394
|  |  |  | 899 | 16.6957
|  |  |  | 900 | 22.2868
|  |  |  | 901 | 19.6969
|  |  |  | 902 | 24.5323
|  |  |  | 903 | 21.9463
|  |  |  | 904 | 23.0235
|  |  |  | 905 | 20.7634
|  |  |  | 906 | 27.8613
|  |  |  | 907 | 22.0987
|  |  |  | 908 | 21.045
|  |  |  | 909 | 18.827
|  |  |  | 910 | 19.6296
|  |  |  | 911 | 17.4413
|  |  |  | 912 | 25.6331
|  |  |  | 913 | 22.272
|  |  |  | 914 | 22.1066
|  |  |  | 915 | 22.0586
|  |  |  | 916 | 25.397
|  |  |  | 917 | 21.2153
|  |  |  | 918 | 25.1729
|  |  |  | 919 | 23.3808
|  |  |  | 920 | 17.1164
|  |  |  | 921 | 17.6686
|  |  |  | 922 | 18.3247
|  |  |  | 923 | 23.0879
|  |  |  | 924 | 20.791
|  |  |  | 925 | 22.8671
|  |  |  | 926 | 21.3582
|  |  |  | 927 | 19.8052
|  |  |  | 928 | 20.9682
|  |  |  | 929 | 19.0166
|  |  |  | 930 | 26.5975
|  |  |  | 931 | 23.0302
|  |  |  | 932 | 22.6985
|  |  |  | 933 | 23.7727
|  |  |  | 934 | 22.4347
|  |  |  | 935 | 18.6928
|  |  |  | 936 | 19.7526
|  |  |  | 937 | 20.6004
|  |  |  | 938 | 21.7751
|  |  |  | 939 | 23.4872
|  |  |  | 940 | 24.7675
|  |  |  | 941 | 20.6506
|  |  |  | 942 | 22.348
|  |  |  | 943 | 24.5563
|  |  |  | 944 | 27.0377
|  |  |  | 945 | 21.0782
|  |  |  | 946 | 16.1414
|  |  |  | 947 | 22.2395
|  |  |  | 948 | 27.2696
|  |  |  | 949 | 19.6887
|  |  |  | 950 | 19.3256
|  |  |  | 951 | 21.2086
|  |  |  | 952 | 22.7853
|  |  |  | 953 | 20.9289
|  |  |  | 954 | 24.382
|  |  |  | 955 | 17.7138
|  |  |  | 956 | 25.0846
|  |  |  | 957 | 21.7022
|  |  |  | 958 | 27.9662
|  |  |  | 959 | 23.0457
|  |  |  | 960 | 22.6479
|  |  |  | 961 | 22.8801
|  |  |  | 962 | 20.5002
|  |  |  | 963 | 20.4457
|  |  |  | 964 | 21.3091
|  |  |  | 965 | 20.2124
|  |  |  | 966 | 24.0456
|  |  |  | 967 | 19.7688
|  |  |  | 968 | 22.1786
|  |  |  | 969 | 22.4896
|  |  |  | 970 | 22.8128
|  |  |  | 971 | 21.524
|  |  |  | 972 | 22.751
|  |  |  | 973 | 20.1362
|  |  |  | 974 | 24.0112
|  |  |  | 975 | 22.0767
|  |  |  | 976 | 22.5661
|  |  |  | 977 | 22.9141
|  |  |  | 978 | 19.0036
|  |  |  | 979 | 25.3042
|  |  |  | 980 | 28.3743
|  |  |  | 981 | 20.0754
|  |  |  | 982 | 23.2153
|  |  |  | 983 | 23.7062
|  |  |  | 984 | 23.6404
|  |  |  | 985 | 21.6204
|  |  |  | 986 | 16.3074
|  |  |  | 987 | 18.3121
|  |  |  | 988 | 19.7138
|  |  |  | 989 | 22.3706
|  |  |  | 990 | 22.4482
|  |  |  | 991 | 26.2017
|  |  |  | 992 | 18.9166
|  |  |  | 993 | 20.4662
|  |  |  | 994 | 23.7219
|  |  |  | 995 | 23.5367
|  |  |  | 996 | 24.2764
|  |  |  | 997 | 20.1627
|  |  |  | 998 | 24.86
|  |  |  | 999 | 22.319
|  |  |  | 1000 | 22.8589
A
B
C
D
E
F
G
H
I
J