## Sheet1
Beta random variable
used to model duration of activity
Fit a beta | in project management
specify alpha beta, min and max
alpha | 2.1963 | mean | 78.4865
beta | 14.5933 | sigma | 47.9675
lower | 0 |  | Data
upper | 600 |  | 26.2566
mean | 78.4865 |  | 91.8403
sigma | 47.9675 |  | 66.5432
transformed mean | 0.13081 |  | 53.8927
transformed var | 0.0063913 |  | 222.4365
72.0544
75.3573
Probability>=200 hours | 0.020502 |  | 78.2742
Probability <=80 hours | 0.58324 |  | 99.0438
Probability between 30 and 150 hours | 0.77106 |  | 90.476
95th percentile of activity duration |  |  | 47.0003
16.2151
117.2774
=BETA.DIST(x,alpha,beta,true,min,max) |  |  | 69.9351
Probability Beta is <=x |  |  | 50.6943
BETA.INV gives percentiles of the Beta random variable